## Sheet1
TCS3 Project Schedule | 2003 | [11 empty] | 2004 | [11 empty] | 2005
| Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
Originial Schedule | 2003 May: Year 1; 2004 Jun: Year 2; 2005 Jun: Year 3 (5 months)
Prelimiary Design (2 months) | bar: 2003 May to 2003 Jun
Procurement (4 months) | bar: 2003 July to 2005 Jan
Development and Testing (10 months) | bar: 2003 May to 2005 Jan
Observatory Preparation (3 months) | bar: 2003 July to 2005 Jan
Installation at observatory (3 months) | bar: 2003 July to 2005 Jan
Testing and Engineering runs (3 months) | bar: 2005 Feb to 2005 Apr
Operational shakedown ( 6 months) | bar: 2005 May to 2005 Oct
Task Milestones
0. Project Overview - May 22, 2003 | bar: 2003 May
1. Conceptual Design - Aug, 2003 | bar: 2003 Jun to 2003 Aug
2. Build TCS3 Computer, controller, t3 electronics, servo simulator | bar: 2003 Sep to 2004 May
3. Encoder Replacement | bar: 2003 Oct to 2004 Mar
4. Install MCC replacement at summit. | bar: 2003 Sep to 2004 Jun
5. Prototype & Build TO Panel | bar: 2003 Sep to 2004 Jun
6. TCS1-TCS3 switch (Drive RA, Dec, and Dome, and Shutter) | bar: 2004 July to 2004 Nov
7. RemoteGUI | bar: 2004 Oct to 2004 Dec
8. Daytime Test & Servo Tuning | bar: 2005 Jan to 2005 Mar
9. Night Engineering (Pointing Run) | bar: 2005 Apr
10. Remove TCS1 | bar: 2005 Aug to 2005 Oct
Milestones Achieved
April 2000 - Started writing description of work estimating cost, manpower, and requirerments for upgrade. Document revised numerious times. Eventually it was submitted as proposal to NASA on June 2001
Grand Awarded June 2002
Project Started - May 2003 | bar: 2003 May
TCS Programmer Hired - May 2003 to Oct 2005 | bar: 2003 May to 2005 Oct
Project Overview Presented to IRTF | bar: 2003 May